## Gant chart
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS | PROJECT DELIVERABLE
SISI системд нэмэлт сайжруулалт хийх | О. Ихбаяр | 2019-02-14 | 2019-05-02 |  | 20%
SCOPE STATEMENT
TASKS | RESPONSIBLE | START | END | DAYS | STATUS
Төслөө сонгох | Бүгд | 2019-02-14 | 2019-02-21 | 7 | Complete
Төслийн санал хүргэх | Бүгд | 2019-02-21 | 2019-02-28 | 7 | Overdue
WBS тодорхойлох | Бүгд | 2019-02-28 | 2019-03-07 | 7 | In progress
Milestone танилцуулах | Бүгд | 2019-03-07 | 2019-03-14 | 7 | Not started
Программын дизайн | Бүгд | 2019-03-14 | 2019-03-21 | 7 | Not started
Техникийн төлөвлөгөө гаргах | Бүгд | 2019-03-14 | 2019-03-21 | 7 | Not started
Дэд бүтэц тодорхойлох | Бүгд | 2019-02-28 | 2019-03-07 | 7 | Not started
Шинэ технологи сурах | Бүгд | 2019-02-21 | 2019-03-28 | 35 | Not started
UI Development | Бүгд | 2019-03-28 | 2019-04-04 | 7 | Not started
DB Development | Бүгд | 2019-03-28 | 2019-04-04 | 7 | Not started
Testing | Бүгд | 2019-04-04 | 2019-04-11 | 7 | Not started
Dev. Complete | Бүгд | 2019-04-11 | 2019-04-18 | 7 | Not started
Hardware Config. | Бүгд | 2019-04-18 | 2019-04-22 | 4 | Not started
System Testing | Бүгд | 2019-04-22 | 2019-04-25 | 3 | Not started
Launch | Бүгд | 2019-04-25 | 2019-05-02 | 7 | Not started
Багшид үзүүлэх | Бүгд | 2019-05-02 | 2019-05-02 |  | Not started

## Stakeholder List
STAKEHOLDER LIST
NAME | POSITION | ROLE IN PROJECT | EMAIL ADDRESS | REQUIREMENTS | EXPECTATIONS
John Smith | VP of Product | Final approval of milestones | john@123.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter

## Cost Baseline
COST BASELINE
ITEM / TASK | % COMPLETE | BASE COST | COST | ACTUAL COST | % BUDGET SPENT
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
COMMUNICATION PLAN
COMMUNICATION TYPE | DELIVERABLE | DESCRIPTION | DELIVERY METHOD | FREQUENCY | OWNER | AUDIENCE
Presentation | 15-minute PowerPoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.